## Instructions
FTE by Month Template
Resource capacity planning for project-driven teams
What this template does
• | Maps FTE demand by role category (Director, Senior, Mid, Junior) across a 24-month horizon.
• | Covers both contracted backlog (100%) and prospective pipeline (weighted by win probability).
• | Aggregates demand across all projects in the Portfolio Summary sheet.
• | Compares total demand to your team's actual headcount by role.
How to use it
• | 1. Set your team capacity on the Portfolio Summary sheet (yellow cells).
• | 2. For each project, open its sheet and enter the project name, status, and win probability.
• | 3. Fill in FTEs by role and month — use decimals (e.g. 0.5 = half an FTE).
• | 4. The Portfolio Summary updates automatically as you fill in projects.
• | 5. Add more project sheets by duplicating 'Project Template' as needed.
Win probability guide
• | Contracted backlog (under contract, work confirmed) → 100%
• | High-probability pursuit (shortlisted, strong relationship) → 70–90%
• | Active pursuit (proposal submitted, competitive) → 40–60%
• | Early pipeline (identified, not yet pursuing formally) → 10–30%
• | The weighted FTE = Required FTE × Win probability.
Color guide
• | Blue inputs: values you enter manually.
• | Green formulas: calculated automatically — do not edit.
• | Yellow cells: key inputs requiring your attention.
• | Red cells in summary: demand exceeds team capacity.

## Portfolio Summary
Portfolio Capacity Summary — FTE by Month
Aggregated FTE demand (probability-weighted) vs team capacity
YOUR TEAM CAPACITY (headcount) | FTEs available
Director | 2
Senior Engineer | 8
Mid Engineer | 20
Junior Engineer | 15
Role / Project | Weighted total | Jan 25 | Feb 25 | Mar 25 | Apr 25 | May 25 | Jun 25 | Jul 25 | Aug 25 | Sep 25 | Oct 25 | Nov 25 | Dec 25 | Jan 26 | Feb 26 | Mar 26 | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26
Director
Project 1 — Water Treatment
Project 2 — Stormwater Study
Project 3 — Pipeline Rehab
Total demand — Director
Team capacity — Director
Gap — Director (+ = surplus, – = shortfall)
Senior Engineer
Project 1 — Water Treatment
Project 2 — Stormwater Study
Project 3 — Pipeline Rehab
Total demand — Senior Engineer
Team capacity — Senior Engineer
Gap — Senior Engineer (+ = surplus, – = shortfall)
Mid Engineer
Project 1 — Water Treatment
Project 2 — Stormwater Study
Project 3 — Pipeline Rehab
Total demand — Mid Engineer
Team capacity — Mid Engineer
Gap — Mid Engineer (+ = surplus, – = shortfall)
Junior Engineer
Project 1 — Water Treatment
Project 2 — Stormwater Study
Project 3 — Pipeline Rehab
Total demand — Junior Engineer
Team capacity — Junior Engineer
Gap — Junior Engineer (+ = surplus, – = shortfall)

## Project 1 — Water Treatment
Project Resource Plan — FTE by Month
Project name | Cincinnati Water Treatment Plant
Status | Backlog
Win probability | 100%
Note: Enter FTEs per role per month. 1.0 = one full-time person.
Role | Weighted total | Jan 25 | Feb 25 | Mar 25 | Apr 25 | May 25 | Jun 25 | Jul 25 | Aug 25 | Sep 25 | Oct 25 | Nov 25 | Dec 25 | Jan 26 | Feb 26 | Mar 26 | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26
Director |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Senior Engineer |  | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1
Mid Engineer |  | 1 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 1
Junior Engineer |  |  | 1 | 1 | 1 | 2 | 2 | 1 | 1
Total FTEs (weighted)

## Project 2 — Stormwater Study
Project Resource Plan — FTE by Month
Project name | Columbus Stormwater Master Plan
Status | Backlog
Win probability | 100%
Note: Enter FTEs per role per month. 1.0 = one full-time person.
Role | Weighted total | Jan 25 | Feb 25 | Mar 25 | Apr 25 | May 25 | Jun 25 | Jul 25 | Aug 25 | Sep 25 | Oct 25 | Nov 25 | Dec 25 | Jan 26 | Feb 26 | Mar 26 | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26
Director |  |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1
Senior Engineer | [5 empty] | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1
Mid Engineer |  |  |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1
Junior Engineer |  |  |  |  | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1
Total FTEs (weighted)

## Project 3 — Pipeline Rehab
Project Resource Plan — FTE by Month
Project name | Cleveland Pipeline Rehabilitation
Status | Prospect
Win probability | 60%
Note: Enter FTEs per role per month. 1.0 = one full-time person.
Role | Weighted total | Jan 25 | Feb 25 | Mar 25 | Apr 25 | May 25 | Jun 25 | Jul 25 | Aug 25 | Sep 25 | Oct 25 | Nov 25 | Dec 25 | Jan 26 | Feb 26 | Mar 26 | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26
Director | [13 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
Senior Engineer | [13 empty] | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 1
Mid Engineer | [13 empty] | 1 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 1
Junior Engineer | [14 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1
Total FTEs (weighted)

## Project Template
Project Resource Plan — FTE by Month
Project name | [Project name]
Status | Prospect
Win probability | 50%
Note: Enter FTEs per role per month. 1.0 = one full-time person.
Role | Weighted total | Jan 25 | Feb 25 | Mar 25 | Apr 25 | May 25 | Jun 25 | Jul 25 | Aug 25 | Sep 25 | Oct 25 | Nov 25 | Dec 25 | Jan 26 | Feb 26 | Mar 26 | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26
Director
Senior Engineer
Mid Engineer
Junior Engineer
Total FTEs (weighted)